## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Estimated Cost
T001 | Project Planning Phase | Jane Smith | 2024-03-15 | 2024-03-25 | 10 | High | In Progress | None | $5,000
T002 | UI/UX Design Finalization | Alex Chen | 2024-03-26 | 2024-04-10 | 15 | High | Pending Approval | T001 | $8,200
T003 | Backend Development | Sam Patel | 2024-04-11 | 2024-05-15 | 35 | Medium | Not Started | T002 | $15,000
T004 | Testing & Quality Assurance | Lisa Wong | 2024-05-16 | 2024-06-10 | 35 | Medium | Not Started | T003 | $7,500
T005 | Deployment & Launch | Mark Jones | 2024-06-11 | 2024-06-15 | 5 | Low | Not Started | T004 | $3,000