## Worksheet
Task Scheduling Income Statement
Task ID | Task Name | Purpose | Assigned To | Scheduled Start Date | Scheduled End Date th> | Status
T001 | Project Planning Meeting | Define project scope and timeline | Jane Smith | 2024-03-15 | 2024-03-18 | In Progress | High
T002 | Market Research Survey | Collect user feedback and insights | Mark Johnson | 2024-03-16 | 2024-03-20 | Pending | Moderate
T003 | UI/UX Design Review | Review and finalize design mockups | Sarah Lee | 2024-03-19 | 2024-03-25 | Not Started | High
T004 | Development Phase Kickoff | Begin coding and integration tasks | David Kim | 2024-03-22 | 2024-04-10 | Scheduled | Medium
T005 | Quality Assurance Testing | Test software for bugs and performance | Lisa Wong | 2024-04-11 | 2024-04-15 | Pending | High