## Worksheet
Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours
Project Planning Meeting | John Doe | 2023-10-01 | 2023-10-02 | In Progress | High | 4.5 | 3
Design Phase Final Review | Alice Smith2023-10-05 | 2023-10-10 | Completed | Moderate | 8 | 8.5
Development Sprint 2 | Robert Lee | 2023-10-11 | 2023-10-18 | Pending | High | 20 | 0
User Testing & Feedback Collection | Sarah Chen | 2023-10-19 | 2023-10-25 | In Progress | Moderate | 15 | 7.5
Final Deployment & Documentation | Michael Brown | 2023-10-26 | 2023-10-30 | Pending | Low | 12 | 0