## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | Dependencies | Resource Allocation
TSK-001 | Project Planning Phase | John Doe | 2024-04-01 | 2024-04-15 | 15 | High | In Progress | None | Full Team
TSK-002 | Market Research & Analysis | Jane Smith | 2024-04-16 | 2024-05-05 | 21 | Medium | Pending | TSK-001 | Marketing Team
TSK-003 | UI/UX Design Finalization | Alex Johnson | 2024-05-06 | 2024-05-31 | 26 | High | Planned | TSK-002 | Design Team
TSK-004 | Backend Development | Sam Kim | 2024-06-01 | 2024-07-15 | 45 | High | Scheduled | TSK-003 | Engineering Team
TSK-005 | Testing & Quality Assurance | Lisa Brown | 2024-07-16 | 2024-08-10 | 35 | Medium | Pending | TSK-004 | QA Team
TSK-006 | Deployment & Launch | Mike Wilson | 2024-08-11 | 2024-08-15 | 5 | High | Planned | TSK-005 | Operations Team