## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Status | Priority | Resource Allocation | Progress (%)
T001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-01 | 1 | Completed | Low | 1 Team Member | 100%
T002 | Requirements Gathering | Jane Smith | 2024-04-02 | 2024-04-15 | 14 | In Progress | Medium | 2 Team Members | 65%
T003 | Design Phase Review | Mike Johnson | 2024-04-16 | 2024-04-30 | 15 | Planned | High | 1 Team Member | 0%
T004 | Development Start | Sarah Lee | 2024-05-01 | 2024-06-15 | 60 | Not Started | High | 3 Team Members | 0%