## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours
T-001 | Project Planning Meeting | John Smith | 2023-10-05 | 2023-10-06 | Completed | High | 4 | 4
T-002 | Design Phase Review | Emily Chen | 2023-10-08 | 2023-10-10 | In Progress | Medium | 8 | 5.5
T-003 | Backend Development | Alex Rivera | 2023-10-12 | 2023-10-25 | Pending | High | 40 | 0
T-004 | User Testing Phase | Sarah Kim | 2023-10-26 | 2023-10-30 | Scheduled | Medium | 20 | 0
T-005 | Final Documentation | David Lee | 2023-11-05 | 2023-11-07 | Not Started | Low | 5 | 0