## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Resource Required | Dependence ID
T001 | Project Kickoff Meeting | John Doe | 2023-10-01 | 2023-10-05 | Completed | High | Project Manager | -
T002 | Requirements Gathering | Jane Smith | 2023-10-06 | 2023-10-15 | In Progress | High | Business Analysts | T001
T003 | Design Phase Final Review | Mike Johnson | 2023-10-16 | 2023-10-20 | Planned | Medium | UI/UX Team | T002
T004 | Development Start | Sarah Lee | 2023-10-21 | 2023-11-05 | Not Started | High | Development Team | T003
T005 | QA Testing Phase | David Brown | 2023-11-06 | 2023-11-25 | Not Started | High | QA Team | T004