## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Duration (Days)
T001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | Completed | Low | 1
T002 | Requirements Gathering | John Smith | 2024-04-02 | 2024-04-15 | In Progress | Medium | 14
T003 | Design Phase Final Review | Alex Johnson | 2024-04-16 | 2024-04-25 | Pending | High | 10
T004 | Development Sprint 1 | Team A | 2024-04-26 | 2024-05-05 | Planned | Medium | 10
T005 | User Testing & Feedback | Sarah Lee | 2024-05-06 | 2024-05-18 | Scheduled | High | 13