## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Dependencies | Resource Allocation | Notes
T001 | System Upgrade Deployment | John Smith | 2024-03-15 | 2024-03-25 | High | In Progress | T002, T003 | IT Team, Servers 1-5 | Ensure all backup systems are in place prior to deployment.
T002 | Network Security Audit | Sarah Lee | 2024-03-18 | 2024-03-28 | High | Scheduled | T001 (completed) | Security Team, Firewall Logs | Review firewall rules and access logs for anomalies.
T003 | User Training Workshop | Michael Chen | 2024-03-20 | 2024-03-21 | Medium | Pending |  | HR & Training Department | Conduct sessions for new system users.
T004 | Server Maintenance | David Park | 2024-03-26 | 2024-03-27 | Low | Planned |  | IT Support Staff | Update software patches and perform diagnostics.