## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Resource Required | Location | Dependencies | Notes
T001 | System Upgrade Deployment | Alex Morgan | 2024-04-01 | 2024-04-15 | High | In Progress | IT Team, Server Admins | Main Data Center, Rack 3 | T002 (Must Complete First) | Ensure all backup systems are active prior to upgrade.
T002 | Database Migration | Jamie Lee | 2024-04-05 | 2024-04-12 | Medium | Scheduled | DBA, Cloud Engineers | Cloud Environment - Region A | T001 (Must Finish) | Backup data verification required post-migration.
T003 | Security Audit Review | Samira Patel | 2024-04-10 | 2024-04-25 | High | Pending Approval | Security Team, Compliance Officers | All Branch Offices & Cloud Systems | T004 (Must Be Completed) | Includes vulnerability scanning and policy compliance checks.
T004 | Employee Training Workshop | Derek Chen | 2024-04-18 | 2024-04-20 | Low | Planned | HR, Training Coordinator | Headquarters Conference Room B |  | Target audience: new staff and IT support personnel.