## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Resource Required | Dependence ID | Notes
TSK-001 | Inventory Audit Setup | Jane Doe | 2024-04-01 | 2024-04-15 | High | Pending | IT Team, Access Tools | - | Ensure access logs are secured and updated.
TSK-002 | Stock Reconciliation | John Smith | 2024-04-16 | 2024-05-10 | Medium | Planned | Warehouse Staff, Counting Tools | TSK-001 | Compare physical stock with system records.
TSK-003 | Inventory System Upgrade | Lisa Brown | 2024-05-11 | 2024-06-30 | High | In Progress | IT Department, Cloud License | - | Include backup plan for system downtime.
TSK-004 | Supplier Onboarding | Mike Taylor | 2024-06-01 | 2024-06-30 | Medium | Scheduled | Purchasing Team, Contracts Package | - | Verify delivery timelines and terms.
TSK-005 | Monthly Report Generation | Sarah Chen | 2024-07-01 | 2024-07-31 | Low | Completed | Finance Team, Reporting Tools | TSK-002, TSK-003 | Include charts and variance analysis.