## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Start Date | Duration (Days) | Resource Required | Notes
T001 | Inventory Audit Preparation | John Smith | 2024-04-15 | High | In Progress | 2024-04-01 | 7 | Finance, IT Support | Complete inventory records review before audit.
T002 | Stock Reconciliation | Sarah Lee | 2024-04-25 | Medium | Not Started | 2024-04-16 | 10 | Warehouse Staff, Logistics | Verify physical vs. system stock levels.
T003 | New Product Onboarding | Mike Chen | 2024-05-10 | High | Planned | 2024-04-26 | 15 | Operations, Marketing, Procurement | Set up product catalog and initiate procurement.
T004 | Equipment Maintenance Schedule | Lisa Wong | 2024-05-30 | Low | Not Started | 2024-05-01 | 30 | Maintenance Team | Routine check of all inventory handling equipment.
T005 | End-of-Quarter Report Compilation | David Kim | 2024-06-15 | Medium | Not Started | 2024-05-16 | 20 | Finance, Data Analysts | Compile KPIs and performance metrics for Q1.