## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Resource Required | Dependencies | Remarks
T001 | Inventory Audit Setup | Jane Smith | 2024-04-01 | 2024-04-15 | In Progress | High | IT Team, Data Analysts | T002, T003 | Verify system access logs.
T002 | Equipment Inventory Update | Mark Johnson | 2024-04-16 | 2024-05-31 | Pending | Moderate | Warehouse Staff, Logistics Manager | T001, T004 | Include all non-functional assets.
T003 | Supplier Contract Review | Sarah Lee | 2024-04-10 | 2024-05-15 | Completed | High | Legal Team, Procurement Office | T001 | All contracts renewed for 2 years.
T004 | Inventory System Upgrade | David Brown | 2024-06-01 | 2024-07-30 | Planned | Critical | IT Department, Cloud Architect | T005, T010 | Must be completed before audit.