## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Resource Required | Dependencies
T-001 | System Backup Deployment | John Smith | 2024-04-01 | 2024-04-05 | High | In Progress | Server Team, IT Admins | None
T-002 | Network Security Audit | Sarah Lee | 2024-04-03 | 2024-04-10 | High | Pending | Security Analysts, Network Engineers | T-001
T-003 | User Training Sessions | Michael Chen | 2024-04-15 | 2024-04-18 | Medium | Planned | Training Coordinators, HR | T-002
T-004 | Cloud Migration Planning | Lisa Wong | 2024-04-20 | 2024-05-10 | Critical | Not Started | Cloud Architects, Project Managers | None