## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Dependents | Remarks
TSK-001 | Inventory Audit | Jane Doe | 2024-04-01 | 2024-04-15 | High | Pending | None | Complete full warehouse review.
TSK-002 | Supplier Onboarding | Mark Smith | 2024-04-10 | 2024-05-01 | Medium | In Progress | TSK-001 | Finalize contracts and update records.
TSK-003 | Stock Reconciliation | Lisa Chen | 2024-04-15 | 2024-04-30 | High | Scheduled | TSK-001 | Verify inventory against system.
TSK-004 | New Inventory System Setup | Team A | 2024-05-01 | 2024-06-15 | Critical | Not Started | TSK-002, TSK-003 | Install and configure new software.