## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Dependencies | Resource Allocation | Notes
TSK-001 | System Setup & Configuration | John Smith | 2024-04-01 | 2024-04-15 | High | Active | None | Server Team, IT Admins | Ensure all hardware and software are properly configured.
TSK-002 | User Access Review | Sarah Lee | 2024-04-10 | 2024-04-20 | Medium | Pending | TSK-001 | Security Team, HR Representatives | Verify user roles and permissions post-system setup.
TSK-003 | Performance Optimization | Mike Chen | 2024-05-01 | 2024-05-31 | High | Planned | TSK-001, TSK-002 | DevOps Team, Cloud Engineers | Conduct benchmarking and tune database queries.
TSK-004 | Training Sessions for Users | Lisa Wong | 2024-05-15 | 2024-05-25 | Medium | Scheduled | TSK-003 | Training Coordinator, Department Heads | Deliver onboarding workshops for all departments.
TSK-005 | Final Audit & Sign-off | Admin Team | 2024-06-01 | 2024-06-15 | Critical | Pending | TSK-003, TSK-004 | Compliance Officer, Audit Team | Final review and formal sign-off from stakeholders.