## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Dependencies | Resource Required | Notes
TSK-001 | Project Initiation Meeting | John Smith | 2023-10-01 | 2023-10-01 | High | Planned | None | Meeting Room, Laptop | First meeting to establish project goals and scope.
TSK-002 | Market Research Collection | Sarah Lee | 2023-10-05 | 2023-10-15 | Medium | In Progress | TSK-001 | Research Team, Survey Tools | Gather data on target audience preferences.
TSK-003 | Design Phase Finalization | Mike Chen | 2023-10-16 | 2023-11-05 | High | Not Started | TSK-002 | Design Software, UI/UX Team | Finalize visual and interactive elements.
TSK-004 | Development Sprint 1 | Alex Rodriguez | 2023-11-06 | 2023-11-20 | High | Planned | TSK-003 | Dev Team, Servers | Build core functionality of the product.
TSK-005 | Quality Assurance Testing | Linda Park | 2023-11-21 | 2023-12-05 | Medium | Not Started | TSK-004 | QA Team, Test Environment | Validate software performance and bugs.