## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Dependencies | Resources Required
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | High | Active | None | Conference Room A, Chair, Project Manager Access
TSK-002 | Requirements Gathering | Mike Johnson | 2024-04-04 | 2024-04-15 | High | Pending | TSK-001 | Stakeholder Interviews, Documentation Tools
TSK-003 | UI/UX Design Phase | Sarah Lee | 2024-04-16 | 2024-05-10 | Medium | Scheduled | TSK-002, TSK-004 | Design Software, Prototyping Tools
TSK-004 | Development Planning | David Brown | 2024-05-11 | 2024-06-15 | <High | Planned | TSK-003 | Code Repository, DevOps Tools
TSK-005 | Testing & QA Cycle | Lisa Wong | 2024-06-16 | 2024-07-10 | High | Not Started | TSK-004 | Automated Test Suite, QA Environment