## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Duration (Days) | Dependencies | Progress (%)
TSK-001 | Design Project Proposal | Jane Smith | 2024-04-01 | 2024-04-15 | High | In Progress | 15 | None | 60%
TSK-002 | Develop Backend API | John Doe | 2024-04-05 | 2024-05-10 | Medium | Planned | 46 | TSK-001 | 0%
TSK-003 | Frontend UI Implementation | Sarah Lee | 2024-04-10 | 2024-05-30 | High | Not Started | 51 | TSK-002 | 0%
TSK-004 | Testing & Quality Assurance | Mike Chen | 2024-05-15 | 2024-06-10 | High | Scheduled | 36 | TSK-003 | 0%
TSK-005 | Final Deployment & Review | Team Lead | 2024-06-15 | 2024-06-30 | Critical | Not Started | 16 | TSK-004 | 0%
Task Scheduling Dashboard - Inventory View