## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Dependencies | Resources Required | Notes
TSK-001 | System Upgrade Planning | Jane Smith | 2024-04-01 | 2024-04-15 | High | In Progress | None | IT Team, Project Manager | Review system logs and create migration plan.
TSK-002 | User Training Session | Mark Johnson | 2024-04-10 | 2024-04-12 | Medium | Scheduled | TSK-001 | Training Room, Presentation Materials | Conduct sessions for new team members.
TSK-003 | Security Audit | Lisa Chen | 2024-05-01 | 2024-05-15 | High | Not Started | TSK-001, TSK-002 | External Auditor, Tools | Evaluate compliance with ISO 27001.
TSK-004 | Server Maintenance | David Lee | 2024-05-20 | 2024-05-25 | Low | Planned | None | IT Technician, Backup Tools | Routine maintenance and log cleanup.