## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependents | Resource Allocation
TSK-001 | Project Initiation | John Smith | 2024-04-01 | 2024-04-15 | On Track | High |  | Full Team
TSK-002 | Market Research | Sarah Lee | 2024-04-16 | 2024-05-10 | In Progress | Medium | TSK-001 | Research Team
TSK-003 | Product Design Finalization | Mike Chen | 2024-05-11 | 2024-06-15 | Pending Approval | High | TSK-002 | Design Team
TSK-004 | Development Phase Start | Anna Patel | 2024-06-16 | 2024-08-31 | Planned | High | TSK-003 | Engineering Team
TSK-005 | Testing & Quality Assurance | David Kim | 2024-09-01 | 2024-10-15 | Scheduled | Medium | TSK-004 | QA Team