## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Dependencies | Notes
TSK-001 | Project Setup & Planning | John Smith | 2024-04-01 | 2024-04-15 | High | In Progress | None | Initial project scope definition and team alignment.
TSK-002 | Resource Allocation | Jane Doe | 2024-04-16 | 2024-04-25 | Medium | Not Started | TSK-001 | Determine team availability and skill mapping.
TSK-003 | Development Phase | Mike Johnson | 2024-04-26 | 2024-05-10 | High | Planned | TSK-002 | Core feature implementation and testing.
TSK-004 | Quality Assurance | Lisa Chen | 2024-05-11 | 2024-05-20 | Medium | Not Started | TSK-003 | Bug testing and user acceptance.
TSK-005 | Deployment & Launch | Robert Kim | 2024-05-21 | 2024-05-31 | High | Not Started | TSK-004 | Go live with client and monitor performance.