## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Dependencies | Notes
TSK-001 | Market Research Setup | Alex Morgan | 2023-10-01 | 2023-10-15 | High | In Progress | None | Gather industry reports and competitor analysis.
TSK-002 | Product Roadmap Draft | Jordan Lee | <>2023-10-162023-11-05 | Medium | Planned | TSK-001 | Align with customer feedback from research.
TSK-003 | UI/UX Design Phase | Sofia Patel | 2023-11-06 | 2023-12-01 | High | Pending Approval | TSK-002 | Design wireframes based on roadmap.
TSK-004 | Development Sprint 1 | Ryan Kim | 2023-12-02 | 2024-01-10 | Critical | Not Started | TSK-003 | Build MVP with core features.
TSK-005 | QA Testing & Feedback Loop | Mia Thompson | 2024-01-11 | 2024-01-30 | Medium | Scheduled | TSK-004 | Conduct beta testing and collect user feedback.