## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Start Date | Duration (Days) | Dependencies
T-001 | Finalize Project Scope Document | John Doe | 2024-04-15 | High | In Progress | 2024-04-01 | 15 | None
T-002 | Design User Interface Mockups | Sarah Lee | 2024-04-25 | Medium | Not Started |  | 10 | T-001
T-003 | Conduct Stakeholder Reviews | Michael Chen | 2024-05-10 | High | Planned | 2024-05-01 | 7 | T-002
T-004 | Develop Backend API Services | Emily Wu | 2024-05-30 | High | Not Started |  | 21 | T-003
T-005 | Deploy to Staging Environment | David Kim | 2024-06-15 | Medium | Scheduled | 2024-06-01 | 14 | T-004