## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Progress (%) | Notes
T001 | Design System UI Mockups | Alex Morgan | 2024-04-01 | 2024-04-15 | In Progress | High | 60% | Final alignment with product team required.
T002 | Backend API Integration | Jordan Lee | 2024-04-05 | 2024-05-10 | Pending | Medium | 25% | Waiting for frontend API schema.
T003 | Database Schema Review | Samira Patel | 2024-04-10 | 2024-04-25 | Completed | Low | 100% | Approved by CTO.
T004 | User Onboarding Flow Testing | Taylor Reed | 2024-04-15 | 2024-05-01 | Not Started | High | 0% | Needs beta group feedback.