## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Remarks
TSK-001 | Project Planning Phase | John Doe | 2024-03-01 | 2024-03-15 | In Progress | High | 40 | 35 | Initial timeline review and stakeholder alignment.
TSK-002 | UI/UX Design Finalization | Sarah Lee | 2024-03-10 | 2024-03-31 | On Hold | Medium | 30 | 0 | Waiting for client feedback on mockups.
TSK-003 | Backend Development | Mike Chen | 2024-04-01 | 2024-05-30 | Not Started | High | 80 | 0 | Requires API integration and database setup.
TSK-004 | Testing & Quality Assurance | Lisa Wang | 2024-06-01 | 2024-06-30 | Scheduled | Medium | 45 | 0 | Include regression and performance testing.
TSK-005 | Deployment to Staging | David Kim | 2024-07-05 | 2024-07-10 | Not Started | Low | 10 | 0 | Final check before production rollout.