## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Resource Allocation
T-001 | Project Planning Workshop | Sarah Johnson | 2024-04-01 | 2024-04-05 | On Track | High | 8 | 6.5 | Team A + External Consultant
T-002 | UI/UX Design Finalization | Mike Chen | 2024-04-06 | 2024-04-15 | In Progress | Medium | 20 | 14.2 | Design Team
T-003 | Backend Development Phase | David Kim | 2024-04-16 | 2024-05-03 | Planned | High | 40 | 0 | Engineering Team
T-004 | QA Testing & Bug Resolution | Lisa Wong | 2024-05-04 | 2024-05-18 | Scheduled | High | 30 | 0 | QA Team + Devs
T-005 | Final Deployment & Training | Rachel Patel | 2024-05-19 | 2024-05-25 | Pending Approval | Medium | 25 | 0 | Support Team + Admin Staff