## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies
T001 | Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-15 | 1 | Completed | High
T002 | Requirement Gathering | Amy Lee | 2024-03-16 | 2024-03-25 | 10 | In Progress | Medium | T001
T003 | Design Phase Finalization | David Chen | 2024-03-26 | 2024-04-05 | 10 | Planned | High | T002
T004 | Development Sprint 1 | Lisa Wang | 2024-04-06 | 2024-04-15 | 10 | Pending | Medium | T003
T005 | Testing & QA Review | Michael Brown | 2024-04-16 | 2024-04-30 | 15 | Planned | High | T004