## Worksheet
Task | Scheduled Start Date | Planned End Date | Duration (Days) | Responsible Party | Priority Level | Status | Dependencies
Loan Application Review | 2024-03-15 | 2024-03-18 | 3 | Loan Officer A | High | Completed | None
Credit Score Verification | 2024-03-19 | 2024-03-21 | 2 | Credit Analyst B | Medium | In Progress | Loan Application Review
Documentation Collection | 2024-03-22 | 2024-03-25 | 3 | Customer Service Team | Medium | Pending | Credit Score Verification
Final Loan Approval | 2024-03-26 | 2024-03-30 | 4 | Loan Committee | High | Not Started | Documentation Collection