## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Priority | Status
T001 | Loan Application Review | 2024-04-01 | 2024-04-05 | 5 | J. Smith | High | In Progress
T002 | <Credit Score Analysis | 2024-04-06 | 2024-04-10 | 5 | A. Johnson | High | Pending
T003 | Documentation Preparation | 2024-04-11 | 2024-04-15 | 5 | M. Lee | Medium | Not Started
T004 | Loan Approval Decision | 2024-04-16 | 2024-04-18 | 3 | S. Brown | Critical | Planned
T005 | Final Client Communication | 2024-04-19 | 2024-04-20 | 2 | C. Davis | Low | Scheduled