## Worksheet
Task | Scheduled Date | Due Date | Priority | Responsible Party | Status
Market Research | 2024-04-01 | 2024-04-15 | High | Sarah Chen | Pending
Business Plan Finalization | 2024-04-05 | 2024-04-25 | High | James Wilson | In Progress
Vendor Onboarding | 2024-04-10 | 2024-05-01 | Moderate | Linda Patel | To Do
Website Launch Preparation | 2024-04-15 | 2024-05-10 | High | Mike Torres | Pending
First Customer Outreach Meeting | 2024-04-20 | 2024-05-15 | Moderate | Emily Clark | Planned