## Worksheet
Month | Task Name | Assigned To | Start Date | End Date | Priority | Status | Estimated Hours | Actual Hours | Progress (%)
January | Project Planning Meeting | Jane Smith | 2024-01-05 | 2024-01-10 | High | Completed | 8 | 8 | 100%
January | Market Research Review | John Doe | 2024-01-15 | 2024-01-20 | Medium | In Progress | 6 | 3 | 50%
February | Design Finalization | Lisa Chen | 2024-02-01 | 2024-02-15 | High | Not Started | 16 | 0 | 0%
February | Development Sprint 1 | Mike Johnson | 2024-02-16 | 2024-03-01 | High | Scheduled | 40 | 0 | 0%
March | User Testing Phase | Sarah Kim | 2024-03-05 | 2024-03-25 | Medium | Planned | 12 | 0 | 0%
Total Tasks |  |  |  |  | 30 | 18 | 12.6%