## Worksheet
Month | Task Name | Assigned To | Start Date | End Date | Priority | Status | Estimated Hours | Actual Hours
January 2024 | Market Research Analysis | John Doe | 2024-01-05 | 2024-01-15 | High | In Progress | 8 | 6
January 2024 | Client Presentation Prep | Sarah Lee | 2024-01-10 | 2024-01-18 | Medium | Not Started | 4 | 0
January 2024 | Website Redesign Proposal | Michael Chen | 2024-01-15 | 2024-01-30 | High | Pending Approval | 16 | 0
February 2024 | User Feedback Session Planning | Emma Wilson | 2024-02-01 | 2024-02-15 | Medium | Scheduled | 6 | 0
February 2024 | Monthly Performance Review | John Doe | 2024-02-18 | 2024-03-01 | Low | Not Started | 4 | 0