## Worksheet
Month | Task Category | Task Name | Scheduled Start Date | Scheduled End Date | Assigned To | Priority Level | Status | Budget (USD) | Actual Spend (USD)
January | Project Planning | Define Project Scope | 2024-01-01 | 2024-01-15 | Jane Doe | High | Completed | 5,000.00 | 4,850.00
January | Resource Allocation | Team Role Assignment | 2024-01-16 | 2024-01-31 | John Smith | Medium | In Progress | 3,000.00 | 2,750.00
February | Development | Build Core Module | 2024-02-01 | 2024-03-15 | Alex Brown | High | Pending | 15,000.00 | 0
February | Testing & QA | Unit Testing Phase | 2024-02-15 | 2024-03-01 | Sarah Lee | Medium | Scheduled | 8,000.00 | 0
March | Review & Approval | Final Documentation Review | 2024-03-01 | 2024-03-15 | Mark Johnson | High | Pending | 2,500.00 | 0
Total Budget |  |  |  | $33,500.00 |  | $24,950.00