## Worksheet
Month | Task Name | Assigned To | Start Date | End Date th> | Priority | Status | Estimated Hours | Actual Hours
January | Project Planning Meeting | John Doe | 2024-01-05 | 2024-01-10 | High | Completed | 8 | 8
January | Design Phase Review | Jane Smith | 2024-01-15 | 2024-01-20 | Medium | In Progress | 6 | 4
February | Development Sprint 1 | Mike Johnson | 2024-02-01 | 2024-02-15 | High | Planned | 36 | 0
February | QA Testing Initiation | Sarah Lee | 2024-02-16 | 2024-03-01 | Medium | Not Started | 16 | 0
March | User Acceptance Testing | David Kim | 2024-03-01 | 2024-03-15 | High | Scheduled | 24 | 0