## Worksheet
Month | Task Categories |  |  |  | Priority | Owner | Status
| Planning | Execution | Review | Adjustment
January | Set quarterly goals | Develop project timelines | Conduct team review | Reassess resource allocation | High | Project Lead | Planned
February | Finalize team assignments | Initiate Phase 1 rollout | Collect feedback from pilot group | Update schedule based on input | Medium | Operations Manager | In Progress
March | Review KPIs from Q1 | Scale Phase 2 implementation | Conduct mid-cycle audit | Adjust priorities for Q2 planning | High | Strategy Director | Pending Review
April | Define Q2 objectives | Train cross-functional teams | Evaluate training effectiveness | Finalize Q2 task roadmap | Medium | HR & Project Office | Scheduled
May | Align departmental plans | Launch new process workflow | Measure performance metrics | Identify bottlenecks and optimize | High | Operations Lead | In Progress
June | Finalize Q3 planning inputs | Complete Phase 3 deployment | Conduct post-implementation review | Document lessons learned | High | Executive Team | Planned
July | Review Q2 performance reports | Begin Phase 4 pilot testing | Assess user adoption rates | Update quarterly forecasts | Medium | Product Manager | Pending Review
August | Refine KPI tracking methods | Scale Phase 4 to full rollout | Conduct customer feedback session | Publish Q3 planning document | High | Data Analytics Team | Scheduled
Quarterly Task Scheduling – Monthly Planner (Q1–Q2)