## Task Scheduling Order Tracker
Task ID | Task Name | Assigned To | Prioritization Level | Due Date | Status th> | Scheduled Start Time th> | Scheduled End Time th> | Progress (%) th> | Dependencies th>
TSK-2024-001 | System Upgrade Deployment | Jane Smith | High | 2024-04-15 | In Progress | 2024-04-10 09:00 | 2024-04-13 17:30 | 75% | Task TSK-2024-003
TSK-2024-002 | User Authentication Review | Michael Chen | Middle | 2024-04-18 | Pending Approval | 2024-04-12 10:30 | 2024-04-15 16:00 | 30% | Task TSK-2024-005
TSK-2024-003 | Database Migration Plan | Sarah Lee | High | 2024-04-16 | Not Started | 2024-04-11 14:00 | 2024-04-17 19:30 | 5% | N/A
TSK-2024-004 | Performance Optimization | David Kim | Low | 2024-05-01 | Planned | 2024-04-25 11:00 | 2024-05-01 13:30 | 0% | Task TSK-2024-006
TSK-2024-005 | Security Audit Checklist | Lisa Wong | High | 2024-04-19Pending Review | 2024-04-13 15:00 | 2024-04-19 18:30 | 25% | N/A