## Worksheet
Task ID | Task Name | Assigned To | Priority | Due Date | Status | Start Date | Estimated Duration (Days) | Progress (%) | Notes
TSK-001 | Project Planning Meeting | Alice Johnson | High | 2023-10-15 | Completed | 2023-10-01 | 3 | 100 | All project milestones reviewed and approved.
TSK-002 | UI/UX Design Finalization | Bob Smith | High | 2023-11-05 | In Progress | 2023-10-10 | 7 | 65 | Design feedback from stakeholders pending.
TSK-003 | Backend Development Phase | Charlie Lee | Medium | 2023-11-20 | Not Started | - | 14 | 0 | Team will begin on first sprint kickoff.
TSK-004 | Performance Testing | Diana Patel | High | 2023-12-01 | Scheduled | 2023-11-30 | 5 | 0 | Preparation of test environment underway.
TSK-005 | Final Deployment Review | Eve Walker | Critical | 2023-12-15 | Blocked | - | 3 | 0 | Dependency on third-party API approval.