## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Start Date | Progress (%)
T001 | Project Requirements Finalization | John Doe | 2024-04-15 | High | In Progress | 2024-03-30 | 75
T002 | UI/UX Design Approval | Jane Smith | 2024-04-20 | Medium | Pending | - | 0
T003 | Backend Development Phase 1 | Alex Johnson | 2024-04-25 | High | Not Started | - | 0
T004 | Testing and Bug Fixing | Sarah Lee | 2024-05-10 | Medium | Scheduled | - | 0