## Worksheet
Task ID | Task Name | Assigned To | Due Date | Status | Priority | Start Date | Estimated Hours | Progress (%) | Notes
TSK-001 | Project Kickoff Meeting | Alex Morgan | 2024-04-15 | Completed | Medium | 2024-04-01 | 2 | 100% | All team members briefed on goals.
TSK-002 | Design Wireframes | Jamie Lee | 2024-04-25 | In Progress | High | 2024-04-03 | 8 | 65% | Final approval pending from UX team.
TSK-003 | Backend Development Setup | Ryan Patel | 2024-05-10 | Scheduled | Medium | 2024-04-10 | 12 | 0% | Waiting for database schema approval.
TSK-004 | User Testing Phase | Samantha Kim | 2024-06-01 | Not Started | High | - | 16 | 0% | Requires final design handoff.