## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependencies | Progress (%) | Notes
TSK-001 | Project Requirements Finalization | Jane Doe | 2024-04-01 | 2024-04-15 | In Progress | High | None | 60%
TSK-002 | UI/UX Design Approval | John Smith | 2024-04-05 | 2024-04-18 | Pending | Medium | TSK-001 | 30% | Feedback due by April 12
TSK-003 | Backend Development Setup | Alex Johnson | 2024-04-10 | 2024-05-01 | Not Started | High | TSK-002 | 0%
TSK-004 | Testing and Quality Assurance | Sarah Lee | 2024-05-05 | 2024-05-25 | Planned | Medium | TSK-003 | 0%