## Worksheet
Task ID | Task Name | Assigned To | Priority | Due Date | Status | Start Date | Estimated Duration (hrs) | Progress (%) | Notes | Action Required
TSK-001 | Design UI Mockups | Jane Smith | High | 2023-10-15 | In Progress | 2023-10-01 | 48 | 75% | Include mobile responsiveness and accessibility features. | Review final mockups by 10/14
TSK-002 | Develop Backend API | Alex Johnson | High | 2023-10-20 | Not Started | - | 60 | 0% | Integrate authentication and payment processing. | Begin development by 10/05
TSK-003 | User Testing & Feedback | Sarah Lee | Medium | 2023-11-05 | Scheduled | 2023-10-18 | 40 | 30% | Recruit 25 users from beta group. | Finalize user pool by 10/25
TSK-004 | Performance Optimization | Michael Brown | Low | 2023-11-15 | Not Started | - | 36 | 0% | Reduce page load time by 30%. | Begin profiling on 10/28
TSK-005 | Documentation & Handover | <Team Lead | Medium | 2023-11-30 | Not Started | - | 24 | 0% | Create full developer guide and user manual. | Complete by 11/20