## Worksheet
Task ID | Task Description | Assigned To | Due Date | Priority | Status | Start Date | Estimated Hours | Actual Hours | Progress (%) | Notes
TSK-001 | Design project layout for Q3 marketing campaign | Anna Smith | 2024-06-15 | High | In Progress | 2024-05-30 | 16 | 12 | 75% | Needs final review from design team.
TSK-002 | Develop API integration with CRM system | James Lee | 2024-07-10 | Critical | Not Started | — | 32 | — | 0% | Requires security audit approval.
TSK-003 | Conduct user testing for mobile app version 2.1 | Sophia Kim | 2024-06-30 | Medium | On Hold | 2024-05-15 | 18 | — | 30% | Waiting for test environment to be ready.
TSK-004 | Prepare quarterly performance report | Marcus Taylor | 2024-06-25 | Low | Completed | 2024-06-10 | 8 | 8 | 100% | Submitted to senior management.