## Worksheet
Task ID | Task Description | Assigned To | Due Date | Priority | Status | Scheduled Start | Estimated Duration (hrs) | Progress (%) | Notes
TSK-001 | Finalize Q3 Marketing Campaign Strategy | Sarah Johnson | 2024-07-30 | High | In Progress | 2024-07-05 | 48 | 65% | Review client feedback from last week.
TSK-002 | Develop User Onboarding Flow | Michael Chen | 2024-08-15 | Medium | Not Started | 2024-07-10 | 36 | 0% | Need UX input from design team.
TSK-003 | Conduct Security Audit on Production System | David Patel | 2024-08-05 | High | Scheduled | 2024-07-25 | 40 | 0% | Must be completed before go-live.
TSK-004 | Update Customer Support Knowledge Base | Lisa Wong | 2024-08-20 | Low | Not Started | 2024-07-30 | 24 | 0% | Include new FAQ for mobile app.
TSK-005 | Coordinate Product Launch Event | Elena Ruiz | 2024-08-30 | High | Preparation Phase | 2024-07-31 | 60 | 40% | Final vendor confirmation pending.