## Worksheet
Task ID | Task Name | Assigned To | Due Date | Status | Priority | Progress % | Next Action
TSK-001 | Design UI Mockups | Sarah Chen | 2024-04-15 | On Track | Medium | 85% | Review with Product Team
TSK-002 | Develop Backend API | James Park | 2024-04-25 | In Progress | High | 60% | Integrate with Auth Module
TSK-003 | User Testing Phase | Linda Wong | 2024-05-10 | Pending | Medium | 0% | Schedule Test Sessions
TSK-004 | Prepare Deployment Plan | Marcus Reed | 2024-05-01 | On Track | Low | 95% | Finalize Rollout Timeline