## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Dependencies | Progress %
TKT-001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-03 | In Progress | High |  | 75%
TKT-002 | Requirements Finalization | Jane Smith | 2024-04-05 | 2024-04-15 | Planned | Medium | TKT-001 | 20%
TKT-003 | UI/UX Design Phase | Alex Johnson | 2024-04-16 | 2024-05-10 | Scheduled | High | TKT-002 | 10%
TKT-004 | Development Sprint 1 | Team A | 2024-05-11 | 2024-06-15 | Pending | High | TKT-003 | 0%