## Worksheet
Task ID | Task Name | Assigned To | Due Date | Status | Priority | Progress (%) | Notes
T001 | User Onboarding Flow Design | Alex Chen | 2024-04-15 | In Progress | High | 65% | Need feedback from UX team by end of week.
T002 | API Integration with Payment Gateway | Jordan Lee | 2024-04-20 | Pending | Critical | 0% | Waiting for backend team to approve environment access.
T003 | Mobile App Beta Launch | Samira Patel | 2024-04-30 | Completed | Medium | 100% | Beta testing concluded with positive user feedback.
T004 | Email Campaign Strategy | Mia Thompson | 2024-05-05 | Planned | Medium | 20% | Draft content in progress. Target audience to be finalized next week.
T005 | Performance Optimization (Backend) | David Kim | 2024-05-10 | In Progress | High | 45% | Optimizing query execution time and database indexing.