## Worksheet
Task ID | Task Name | Assigned To | Due Date | Status | Priority | Progress (%) | Next Action
TSK-001 | Finalize Project Scope Document | Sarah Chen | 2024-04-15 | On Track | High | 85% | Review with stakeholders by 04/10
TSK-002 | Develop User Interface Mockups | James Rivera | 2024-04-25 | In Progress | Medium | 40% | Submit draft for feedback by 04/12
TSK-003 | Conduct System Integration Testing | Lisa Park | 2024-05-10 | Pending | High | 0% | Schedule test environment setup on 04/18
TSK-004 | Prepare Training Materials | Mike Thompson | 2024-05-05 | Not Started | Medium | 0% | Begin content outline by 04/20
TSK-005 | Finalize Budget Approval | Anna Rodriguez | 2024-04-30 | On Track | High | 95% | Submit for CFO review by 04/28