## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Start Date | Progress (%) | Notes
T-001 | Design Project Proposal | Team Lead A | 2024-04-15 | High | In Progress | 2024-04-01 | 65% | Finalize scope and gather stakeholder input.
T-002 | Develop User Interface Mockups | Designer B | 2024-04-25 | Medium | Not Started | — | 0% | Review with product team for alignment.
T-003 | Backend API Integration | Developer C | 2024-05-10 | High | Scheduled | 2024-04-10 | 30% | Integrate payment gateway endpoints.
T-004 | Conduct User Testing Session | QA Lead D | 2024-05-15 | Medium | Planned | 2024-04-30 | 0% | Recruit 15 participants; schedule sessions.
T-005 | Finalize Documentation | Writer E | 2024-04-30 | Low | Completed | 2024-04-18 | 100% | Submitted to compliance team.