## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Progress (%) | Notes
TSK-001 | Project Requirements Review | John Doe | 2024-04-01 | 2024-04-15 | In Progress | Medium | 65% | Review with stakeholders and finalize scope.
TSK-002 | UI/UX Design Finalization | Sarah Lee | 2024-04-05 | 2024-04-25 | Pending | High | 30% | Waiting for feedback from product team.
TSK-003 | Backend Development Phase | Mike Chen | 2024-04-10 | 2024-05-10 | Not Started | High | 0% | Initial setup and API integration.
TSK-004 | Performance Testing | Lisa Wong | 2024-05-01 | 2024-05-15 | Planned | Medium | 0% | Run load and stress tests on staging environment.